## Feature List Burndown 3 Oct 16
Iteration 1 | 3rd Oct 2016 - 16th Oct 2016 |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Task ID | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | Plan with supervisor/customer | Must | 1.1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5
| Detailed planning on own | Must | 1.2 | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
2. Literature review | Draft the literature review | Must | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tidy up the references | Should | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revise conclusion | Must | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Project Risk | Review project scope | Must | 3.1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Examine high likelihood impact risks | Should | 3.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review options for decisions | Should | 3.3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revise risk table | Could | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Report | Project Proposal Report | Must | 4.1 | 10 | 0 | 3 | 2 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 10
5. Iteration Review | Quality Review | Must | 5.1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sign off | Must | 5.2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review iteration | Must | 5.3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Ideal - remaining work effort in Ideal hours |  |  |  | 25.5 | 22.95 | 20.4 | 17.85 | 15.3 | 12.75 | 10.2 | 7.65 | 5.1 | 2.55 | -3.5527e-15
Actual - remaining effort in Ideal hours |  |  |  | 25.5 | 24.5 | 20.5 | 18.5 | 17.5 | 15.5 | 15.5 | 13.5 | 11 | 11 | 9
| Reason for missing target effort: | This is a backlog of the effot I have applied and so is not 100% accurate

## Feature List Burndown 17 Oct
Iteration 2 | 17th Oct 2016 - 30th Oct 2016 |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Task ID | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | Plan with supervisor/customer | Must | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Detailed planning on own | Must | 1.2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Literature review | Draft the literature review | Must | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tidy up the references | Should | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revise conclusion | Must | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Project Risk | Review project scope | Must | 3.1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Examine high likelihood impact risks | Should | 3.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review options for decisions | Should | 3.3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revise risk table | Could | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Report | Project Proposal Report | Must | 4.1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Iteration Review | Quality Review | Must | 5.1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sign off | Must | 5.2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review iteration | Must | 5.3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  |  | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
Actual - remaining effort in Ideal hours |  |  |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Reason for missing target effort: |  | This is a backlog of the effot I have applied and so is not 100% accurate

## Feature List Burndown 31 Oct
Iteration 3 | 31st Oct 2016 - 13th Nov 2016 |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Task ID | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | Plan with supervisor/customer | Must | 1.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| Detailed planning on own | Must | 1.2 | 3 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
2. Literature review | Draft the literature review | Must | 2.1 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0 | 1.5
| Tidy up the references | Should | 2.2 | 0.5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1.5
| Revise conclusion | Must | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Project Risk | Review project scope | Must | 3.1 | 2 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 3
| Examine high likelihood impact risks | Should | 3.2 | 2 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
| Review options for decisions | Should | 3.3 | 2 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
| Revise risk table | Could | 3.4 | 2 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
4. Report | Project Interim Report | Must | 4.1 | 10 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 7
5. Iteration Review | Quality Review | Must | 5.1 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sign off | Must | 5.2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review iteration | Must | 5.3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  |  | 30.5 | 27.45 | 24.4 | 21.35 | 18.3 | 15.25 | 12.2 | 9.15 | 6.1 | 3.05 | -4.4409e-15
Actual - remaining effort in Ideal hours |  |  |  | 30.5 | 27.5 | 27.5 | 19 | 16 | 15.5 | 15.5 | 15.5 | 14.5 | 10.5 | 10.5

## Feature List Burndown 14 Nov
Iteration 4 | 14th Nov 2016 - 27th Nov 2016 |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Task ID | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | Plan with supervisor/customer | Must | 1.1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Detailed planning on own | Must | 1.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Literature review | Draft the literature review | Must | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tidy up the references | Should | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revise conclusion | Must | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Project Risk | Review project scope | Must | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Examine high likelihood impact risks | Should | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review options for decisions | Should | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revise risk table | Could | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Report | Project Interim Report | Must | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Iteration Review | Quality Review | Must | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sign off | Must | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review iteration | Must | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  |  | 1.5 | 1.35 | 1.2 | 1.05 | 0.9 | 0.75 | 0.6 | 0.45 | 0.3 | 0.15 | 0
Actual - remaining effort in Ideal hours |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5

## Project Feature List
| ID | Feature / Task / Deliverable | Priority | Planned Iteration | Actual Iteration | Total Planned Effort | Total Actual Effort | Complete? | Issues / Log | Priority List
3rd Oct | 1 | Iteration Planning | Must | 1 | 1 | 3 | 2.5 | Y | Backlog of each task | Must
| 3 | Project Brief Report | Should | 1 | 1 | 6 | 4 | Y | Backlog of each task | Should
| 5 | Project Proposal Report | Must | 1 | 1 | 3 | 4 | Y | Backlog of each task | Could
| 4 | Iteration Review | Must | 1 | 1 | 7 | 2 | Y | Backlog of each task
17th Oct | 1 | Iteration Planning | Must | 2 | 2 | 3 | 0 | Y | Backlog of each task
| 3 | Project Brief Report | Should | 1 | 2 | 2 | 0 | N | Backlog of each task
| 6 | Interim report | Must | 2 | 2 | 2 | 0 | N | Backlog of each task
| 4 | Iteration Review | Must | 2 | 2 | 3 | 0 | Y | Backlog of each task
31st Oct | 1 | Iteration Planning | Must | 3 | 2, 3 |  |  |  | Organising tasks and format
| 6 | Interim report | Must | 3,4 | 3 |  |  |  | I've made good progress
| 7 | Design of application | Should | 3,4
| 4 | Iteration Review | Must | 3
14th Nov | 1 | Iteration Planning | Must | 4
| 6 | Interim report | Must | 3,4 | 3,4
| 9 | Research alarms apps | Should
| 7 | Design of application | Must | 3,4
| 8 | Prototypes | Must | 4,5
| 4 | Iteration Review | Must | 4
28th Nov | 1 | Iteration Planning | Must | 5
| 8 | Prototypes | Should
| 10 | Research how to develop an alarm for android
| 11 | Design a basic alarm application
| 12 | Research some form of web interaction to deal with lightbulb commands |  | 11, 12
| 13 | Develop some form of web interaction to deal with lightbulb commands
| 14 | Integrate web interaction into alarm functionality
| 15 | Research how to physically display smartbulb interaction (Arduino, raspberry pi, actual smart bulb)

## DeliverablesTasks
ID | Name
1 | Iteration Planning
2 | Project Risk
3 | Project Brief Report
4 | Iteration Review
5 | Project Proposal Report
6 | Interim report
7 | Design of application
8 | Prototypes
9 | Research alarms apps
10 | Research how to develop an alarm for android
11 | Design a basic alarm application
12 | Research some form of web interaction to deal with lightbulb commands
13 | Develop some form of web interaction to deal with lightbulb commands
14 | Integrate web interaction into alarm functionality
15 | Research how to physically display smartbulb interaction (Arduino, raspberry pi, actual smart bulb)